

GSA Transition Coordination Center

**TRANSITION HANDBOOK**

NETWORX, WITS 3, AND GSA REGIONAL LOCAL SERVICES TO ENTERPRISE INFRASTRUCTURE SOLUTIONS (EIS) CONTRACTS

Version 7.1

June 28, 2022

DTID #: TCC2-ASC-0068-202200608-7

PREPARED FOR

Transition Coordination Center

General Services Administration

Federal Acquisition Service

1800 F Street NW

Washington, DC 20405

Contract Number: GS00Q12NSD0002

Order Number: 47QTCB20F0073

This document is hereby authorized for release by the General Services Administration.

Acting Executive Director, Office of Enterprise Technology Solutions

Information Technology Category

General Services Administration

Table of Contents

[1 Purpose 1](#_Toc107325275)

[2 Background 1](#_Toc107325276)

[3 Successful Transition 2](#_Toc107325277)

[3.1 Involvement of the Agency’s highest levels and key functional areas 2](#_Toc107325278)

[3.2 Agency Transition Plan 3](#_Toc107325279)

[3.3 Early and effective support from GSA to Agencies 3](#_Toc107325280)

[3.4 Phased, orderly approach 3](#_Toc107325281)

[3.5 Transparency and meaningful reporting 3](#_Toc107325282)

[4 Transition Overview 3](#_Toc107325283)

[4.1 Transition Approach 4](#_Toc107325284)

[4.2 Transition Sequence of events 5](#_Toc107325285)

[5 Roles and Responsibilities 6](#_Toc107325286)

[5.1 Agency Transition Sponsor 6](#_Toc107325287)

[5.2 Agency Transition Managers 7](#_Toc107325288)

[5.3 Ordering Contracting Officers 8](#_Toc107325289)

[5.4 GSA Full Service (Regional Local Services) 8](#_Toc107325290)

[6 Lessons Learned from Previous Transitions 9](#_Toc107325291)

[7 Transition Planning 9](#_Toc107325292)

[7.1 Identify Key Agency Personnel 9](#_Toc107325293)

[7.2 Confirm Inventory 10](#_Toc107325294)

[7.3 Define Requirements and Order Placement Process 11](#_Toc107325295)

[7.4 Arrange for GSA Assistance 12](#_Toc107325296)

[7.4.1 GSA-Assisted Transition 12](#_Toc107325297)

[7.4.2 Transition Assistance 12](#_Toc107325298)

[7.4.3 GSA TCC Training Plan 13](#_Toc107325299)

[8 Transition Management and Implementation 13](#_Toc107325300)

[8.1 Develop Fair Opportunity Solicitations 13](#_Toc107325301)

[8.2 Award Task Orders 14](#_Toc107325302)

[8.3 Ordering Process 14](#_Toc107325303)

[8.4 Service Implementation 14](#_Toc107325304)

[8.5 Transition Tracking and Reporting 15](#_Toc107325305)

[8.6 Stakeholder Communications for Transition 16](#_Toc107325306)

[8.6.1 Infrastructure Advisory Group 16](#_Toc107325307)

[8.6.2 Help Desk 16](#_Toc107325308)

[8.6.3 EIS Transition Website 16](#_Toc107325309)

[8.6.4 EIS Bulletins 16](#_Toc107325310)

[8.7 Disconnects 17](#_Toc107325311)

[9 Summary 17](#_Toc107325312)

[Appendix A – Acronym List 18](#_Toc107325313)

[Appendix B – Agency Transition Plan Outline 20](#_Toc107325314)

[Appendix C – List of FTS2001 to Networx Lessons Learned 23](#_Toc107325315)

[Appendix D – Sample Dashboard Reports for Large and Medium Agencies’ Transition Progress 29](#_Toc107325316)

[Appendix E – Agency Transition Checklist 31](#_Toc107325317)

[Appendix F – Transition Order Sequencing 35](#_Toc107325318)

[Appendix G – Cutover Guidance 40](#_Toc107325319)

DOCUMENT CHANGE HISTORY

|  |  |  |  |
| --- | --- | --- | --- |
| Version | Date | Description | Prepared by |
| 1.0 | 8/22/14 | Original Issue | Debbie Hren |
| 1.1 | 4/8/16 | Updated | Joe Hester |
| 1.2 | 4/27/16 | Updated – incorporated GSA feedback from 4/15 email | Chuck Brock |
| 1.3 | 5/4/16 | Updated – incorporated GSA feedback from 5/03 meeting | Chuck Brock |
| 1.4 | 5/5/16 | Edits for revised submission | Tatia Sheptock |
| 2.0 | 5/31/16 | DRAFT Routed for NSP and Acquisition Operations review | Debbie Hren |
| 2.0 | 6/8/16 | Final version routed to Amando for authorization to release | Charles Martin |
| 3.0 | 9/19/16 | Edited to reflect GSA realignment and new schedule for EIS contract award. Additional detail provided on how to submit ATPs in Sections 4.1 and 7. *This version not published external to TCC.* | Scott Sizemore |
| 4.0 | 3/10/17 | Updated to reflect GSA realignment, shared FTS2001 to Networx lessons learned; updated for MOPS and ordering guides; provided sample dashboard reports; added Transition Checklist. *This version not published external to TCC.* | Debbie Hren/Scott Sizemore |
| 4.1 | 5/4/17 | Expanded Transition Checklist in Appendix E, updated Full Service transition Section 5.4, and added description of All Agency Inventory Section 7.2. Version submitted for OTS CCB review. | Tatia Sheptock/Debbie Hren |
| 5.0 | 11/14/17 | Incorporated changes to EIS Transition Timeline and phase gate target dates and changes to full service transition. Included various edits from OTS CCB review. | Debbie Hren |
| 6.0 | 6/27/19 | Added Appendices F and G; Updated transition timeline; Added EIS Bulletins in Section 8.6; numerous, minor editorial edits | Scott Sizemore |
| 6.5 | 8/27/19 | Edited terminology for accuracy | Debbie Hren |
| 7.0 | 6/8/22 | Updated background to include the continuity of service period; Updated terminology from previous GSA reorganization throughout; Updated Transition Timeline; Updated Section 7.4 to include available agency support and training resources; Updated EIS RFP location to SAM.gov; Added third party contracting support as a consideration in Table F-1 (Appx F) | Chris Hamby/Tatia Sheptock |
| 7.1 | 6/28/22 | Minor edits resulting from review of v 7.0 | Debbie Hren |

# Purpose

The General Services Administration (GSA) developed this handbook for agencies and other stakeholders to facilitate a successful, timely, and orderly transition of services from the expiring Networx, Washington Interagency Telecommunications Systems (WITS) 3, and GSA Regional local service contracts to the Enterprise Infrastructure Solutions (EIS) contracts.

This document advocates the importance of coordination and cooperation among transition stakeholders. This is achieved by (1) defining a standardized approach for all agencies across the government, (2) recommending a sequence of transition events, (3) describing transition roles and responsibilities, and (4) providing guidance on transition processes and procedures from the agencies’ perspective. This handbook provides a framework for agencies to manage a successful transition by describing the essential activities to prepare for, execute, and track transition. It includes an overview of activities agencies perform to order services under the new contracts and complete their transitions.

# Background

GSA’s Network Services 2020 (NS2020) Strategy represents a portfolio of contracts that provide the flexibility and agility to support agency migrations to future technologies while adhering to the high-level objectives laid out in the Information Technology (IT) Reform Plan and Digital Government Strategy. NS2020 enables interoperability and furthers the migration from legacy technologies to a converged Internet Protocol (IP) environment with common, core security standards through an expansive array of modern telecommunications and IT service offerings. As part of the “Infrastructure Solutions” component of NS2020, the EIS contracts provide high-quality telecommunications and network services and solutions that meet or exceed agency requirements, conform to government policies and standards, and offer competitive pricing. EIS provides continuous competition to satisfy specific networking projects, emerging requirements, technology refreshment, and access to innovative solutions. The combination of more services, greater competition, and improved performance provides significant incentive to transition to EIS.

In October 2018, GSA announced it intends to extend the expiring telecommunications contracts to further enable modernization and transition execution, pending commitment by agencies to maintain momentum on EIS transition and network modernization. With this extension, all contracts will expire in May 2023.

In February 2022, GSA announced it intends to invoke the continuity of service (CoS) clause for the expiring contracts. This provides agencies the opportunity to either complete transition to EIS or find another solution to prevent interruption of services. Invoking the CoS clause helps reduce the risks associated with not completing transition by the May 2023 contract expiration date. It also provides more time for agencies to address challenges resulting from delayed TO awards, supply chain disruptions, and other important priorities. To take advantage of the CoS period, an agency must sign a Memorandum of Understanding (MOU) with GSA by September 30, 2022. At the end of the 12-month CoS period (May 31, 2024), any remaining active services on the expiring contracts will be disconnected in accordance with the terms and conditions of their respective contracts. GSA will remove agencies that do not sign the MOU from the Networks Authorized Users List (NAUL) for the expiring contracts in October 2022. Contractors will then begin the disconnect process as early as November 2022 and complete it no later than May 2023. See [gsa.gov/eistransition](http://gsa.gov/eistransition) for more information on the transition timeline.

# Successful Transition

In addition to the benefits of transitioning to EIS, stakeholders must be mindful of the critical schedule for completing transition. GSA is committed to supporting agencies through transition; however, it is up to the agencies to execute transition before the Networx, WITS 3, and GSA Regional local service contracts expire or the CoS period ends (as applicable), either by competitively ordering replacement services on EIS or by justifying a sole-source action to move existing services from the current provider’s Networx, WITS 3, and GSA Regional local service contracts to their EIS contract, if that is available.

The transition process is subject to significant risks, including that the current service provider is not awarded an EIS contract or selected through the Fair Opportunity (FO) process and that the selected service provider is unable or unwilling to execute all transition requirements as expected or within the timeline to avoid gaps in service continuity. Agencies should not expect further extension of the expiring contracts and plan to complete transition by September 2022 or consider alternative approaches to avoid service gaps. GSA advises the agency to carefully review and consider the guidance offered in this Transition Handbook, the Fair Opportunity and Ordering Guide (FOOG), and the EIS Management and Operations (MOPS) Handbook as well as other training and guides available on [gsa.gov/eis](http://gsa.gov/eis) and [gsa.gov/eistransition](http://gsa.gov/eistransition), particularly noting the lessons learned from previous transitions and how they can be incorporated into the transition to EIS. The agency must establish and maintain effective oversight throughout transition, and escalate problems with the service providers to GSA with documentation.

In concert with agency customers, contractors, and oversight organizations, GSA is implementing a transition strategy that capitalizes on lessons learned from previous transitions to affect a successful transition. The key elements of this strategy follow.

* 1. Involvement of the Agency’s highest levels and key functional areas

The engagement of executive management is critical to secure and focus the resources across the agency to plan and implement the transition, to track progress, and to respond to risks. GSA asks each agency to identify, by name, an executive sponsor for the transition. Another fundamental requirement is early assignment of a Lead Transition Manager (LTM) and a Transition Ordering Contracting Officer (TOCO) that understands the Federal Acquisition Regulation (FAR) and the agency’s policies for selecting a contractor, and has a repertoire of workable approaches to meet the agency’s transition requirements.

* 1. Agency Transition Plan

Agencies must develop a transition plan and provide it to GSA. GSA will track this as a critical milestone to be completed by October 2016, with updates and additional detail as needed throughout transition. Agencies should plan with sufficient flexibility to coordinate transition with other ongoing activities regardless of the impact of external events. For example, a change of presidential administration could have significant impact, and agencies’ plans should consider the impact.

* 1. Early and effective support from GSA to Agencies

From the earliest agency engagements, GSA will provide tailored support to each agency appropriate to its transition approach, especially for the contractor selection, or FO process (see FAR Subpart 16.505). GSA will work with the existing Networx, WITS 3, and GSA Regional local service contractors to conduct the initial validation of inventory and maintain the inventory throughout transition. GSA will provide training for ordering on the EIS contracts based on the EIS FOOG available on [gsa.gov/eistransition](http://gsa.gov/eistransition).

* 1. Phased, orderly approach

GSA will coordinate with agencies and contractors to develop a recommended sequence of transition orders to achieve early progress, level resource demands, and minimize backlogs. GSA will work with all stakeholders to guide transition through this sequence. See Appendix F for information on sequencing transition orders, including attributes of services to transition and other items to consider during transition.

* 1. Transparency and meaningful reporting

GSA will define and openly track major milestones and report agencies’ progress to the Office of Management and Budget (OMB). Measures of transition progress will be developed in collaboration with agencies and contractors and will be representative of business volume and the complexity of services being moved.

# Transition Overview

Transition is a critical component of a larger agency evolution where agencies upgrade their network equipment and architecture to reflect new applications, new security approaches, increased traffic, and potentially changing network traffic patterns.

For the purposes of this handbook, transition is defined as the movement of services from the expiring Networx, WITS 3, and GSA Regional local service contracts to EIS and continues until all services have been disconnected. Transition planning, execution, and management activities are critical to a successful transition to EIS and require participation by all relevant stakeholders. Agencies using Networx, WITS 3, and GSA Regional local service contracts have the primary responsibility for completing transition successfully; accordingly, they should have an executive level sponsor for the agency’s transition.

GSA, as the owner of the contracts, executes activities necessary for transition through three integrated functions: the Program Management Office (PMO), customer engagement, and the Transition Coordination Center (TCC). The PMO supports the agencies’ transition by establishing the EIS vehicles and managing the contractors. Customer engagement is responsible for ensuring that appropriate and effective support is provided to each agency during their transition to EIS. Within the customer engagement function, each agency is assigned a Solutions Broker (SB) listed on [gsa.gov/nspsupport](http://gsa.gov/nspsupport), and that SB has overall responsibility for the management of GSA support to that agency. Any other GSA organization providing support to an agency (such as the TCC) works with oversight from the SB. The TCC provides Government-wide transition planning, execution, progress tracking, and reporting. GSA established the TCC, which is staffed by both GSA and contractor personnel, to assist and support agencies with the movement of services from the expiring contracts to EIS. The TCC interacts extensively with agencies, existing contractors, EIS contractors, and oversight organizations such as the OMB and Government Accountability Office (GAO).

* 1. Transition Approach

In its report GAO-06-476, TELECOMMUNICATIONS: Full Adoption of Sound Transition Planning Practices by GSA and Selected Agencies Could Improve Planning Efforts, June 2006, the GAO identified the following best practices for conducting effective transition planning:

1. Establish an accurate telecommunications inventory and an inventory maintenance process

2. Perform a strategic analysis of telecommunications requirements and use this to shape the agency’s management approach and guide efforts when identifying resources and developing a transition plan

3. Establish a structured management approach that includes a dedicated transition management team that will use clear lines of communications in addition to key management processes, such as project management, configuration management, and change management

4. Identify the funding and human capital resources that the transition effort will require

5. Develop a transition plan that includes transition objectives, measures of success, risk assessment, and a detailed timeline

In a subsequent audit of transition practices, GAO reported in GAO-14-63, *TELECOMMUNICATIONS: GSA Needs to Share and Prioritize Lessons Learned to Avoid Future Transition Delays*, December 2013, that each agency should treat the transition as a “critical project.” As such, the agency should develop a transition project management plan that includes “a timeline of all activities that need to be completed, taking into account priorities relative to the agency’s mission critical systems, contingency plans, and identified risks.” Agencies’ transition teams, including project managers, telecommunications specialists, and contracting officers, should develop the Agency Transition Plan (ATP) and coordinate with executive leadership, such as the Chief Information Officer (CIO) as executive sponsor and other executives such as the Chief Financial Officer, Chief Acquisition Officer, and Chief Human Resources Officer as appropriate. An outline to the ATP is included in Appendix B to facilitate this process. The Agency Transition Sponsor must e-mail the ATP to the TCC at eistcc.ta@gsa.gov by October 2016. The TCC will provide it to the GSA’s Assistant Commissioner of Federal Acquisition Service (FAS)/Information Technology Category (ITC) and to OMB. The standardized format and required delivery ensure all stakeholders—including and especially the contractors--are aware of the agency’s plan and can better support meeting the agency’s objectives in conjunction with the overall objectives of the transition program.

* 1. Transition Sequence of events

To keep the focus on timely transition, GSA has identified critical milestones for agencies to meet. These, along with other common steps in transition, comprise the following activities necessary for agencies to successfully complete transition:

* PRIOR TO AWARD OF EIS CONTRACTS
* Develop funding requirements and coordinate with agency budget submissions for fiscal year (FY) 2017 – 2023. Task Orders (TOs) on EIS require funding at the time of issue; therefore, it is critical that agencies budget for installation charges for services on EIS starting in FY17, and for monthly services starting in the fiscal year services are anticipated to begin. GSA can help estimate those charges and advise on strategies to minimize the cost to the agencies. For additional information, contact your SB.
* Identify the Agency Transition Sponsor
* Understand EIS services, management and operations requirements, and pricing structures; become familiar with the EIS Request for Proposal (RFP) (see [gsa.gov/eis](http://gsa.gov/eis)) and subscribe to Interact at <https://interact.gsa.gov/>eis for real-time notifications of updates
* Appoint both a LTM and TOCO and identify the transition organization (see Section 5, Roles and Responsibilities)
	+ Confirm existing Networx, WITS 3, and GSA Regional local service inventories to ensure they are accurate and current by October 2016; for instructions go to gsa.gov/eis
	+ Evaluate current technical solutions and develop transition planning for target technical solutions, including upgrades, transformations, retirement, or other changes
	+ Develop ATP by October 2016 that clearly identifies the number of FO solicitations for transition, incremental transition costs, and a schedule for transition. Specifying FO plans or solicitation forecasts will help agencies manage the work, and sharing those plans with GSA and the EIS contractors will allow greater collaboration and management of resources for all involved. Agencies should provide their SBs an updated solicitation forecast and estimated release date(s) by July 2017 and any updates thereafter as required.
	+ Estimate human resource requirements and coordinate with agency staffing and training plans for FY 2016-2023
	+ Initiate solicitations for the FO process to select EIS contractors, such as RFPs for complex requirements and RFQs for simple requirements
	+ Execute an Interagency Agreement (IAA) with GSA for assistance, as applicable.
* AFTER AWARD OF EIS CONTRACTS
	+ Attend training and receive a Delegation of Procurement Authority (DPA) from GSA to agency Ordering Contracting Officers (OCOs)
	+ Conduct FO selection of contractor(s) and award fully-funded TOs
	+ Update ATP as appropriate and share with GSA
	+ Provide GSA with updates as the forecast for FO solicitations changes or at least quarterly beginning in July 2017. GSA will share these solicitation forecasts with EIS contractors to allow them to plan for responding.
	+ Order services for transition on EIS
	+ Prepare for service cutover
	+ Order disconnects on Networx, WITS 3, and GSA Regional local service contracts.

Figure 1 depicts a sequence of events and deadlines for agencies to successfully accomplish transition activities. Note that in order to expedite the FO process, agencies are advised to begin preparing their solicitations in advance of EIS award and expect to issue those solicitations to industry as soon as possible after award. A detailed list of transition activities for agencies is provided in Appendix E – Agency Transition Checklist.



Figure 1. *Transition Sequence of Events*

# Roles and Responsibilities

This section describes the roles and responsibilities of key personnel for transition to EIS.

* 1. Agency Transition Sponsor

Each agency should have an executive level manager that sponsors the agency’s transition project; the lessons learned in previous transitions highlight the need for this support. The sponsor likely would be the CIO or executive of the organization to which the transition manager and team report or that otherwise has influence to secure the financial and human resources for the transition. The sponsor serves as a spokesperson to senior agency leadership, is the primary interface and partner to GSA executives, and is the agency’s representative accountable to oversight organizations, such as OMB. Important activities for the Agency Transition Sponsor include approving the agency’s ATP and serving as an escalation path. For department level agencies, the sponsor should represent all components within the department.

* 1. Agency Transition Managers

Each agency should have an LTM and may also designate other supporting transition managers (TMs). A TM is a Government employee (or appointed contractor) who leads the planning, management, and implementation of the agency’s transition of services from Networx, WITS 3, and GSA Regional local service contracts to EIS. The LTM develops the ATP; acts as the central point of contact to GSA’s TCC; executes, tracks, and reports transition activities; and escalates issues to GSA as appropriate. In GAO-14-63, GAO reported that “weaknesses in agencies’ project planning also contributed to the delays” in the transition to Networx. Therefore, the LTM must have strong project management, communications, and interpersonal skills and be a recognized leader within the agency.

The process for establishing a transition team starts with the Agency Transition Sponsor designating the LTM for the agency. The sponsor communicates this designation to GSA. The LTM may then designate other supporting TMs for the agency.

Agency TMs:

* Engage agency staff to address requirements
* Provide overall project management of the agency’s transition to EIS, including meeting milestone deadlines and managing project risks
* Plan and prepare agency-specific transition strategies and the ATP along with more detailed plans as needed
* Execute, track, and report on activities of the overall transition to ensure that the Agency Transition Sponsor, agency management, GSA, and oversight groups are well aware of the status and any jeopardies to meeting the schedule
* Identify the Agency Bureau (AB) codes that fall under the authority of the agency, any hierarchical organization of those codes, and the mapping of Agency Hierarchy Codes (AHCs) to AB codes
* Confirm the agency’s inventory of services to transition
* Ensure transition orders are placed in a timely fashion; prioritize orders for services that have lengthy or complex installations
* Anticipate the possibilities of changing service providers or services (such as changing connectivity requirements or solutions other than like-for-like replacement) during the transition effort and mitigate those factors in transition plan(s)
* Build time into transition plans to allow time for contract modifications, if needed
* Serve as the interface to the GSA TCC
* Coordinate training by GSA for the agency’s transition team and support personnel
* Escalate issues to GSA, the EIS contractors, or agency management and Agency Transition Sponsor as appropriate
* Submit or validate and forward requests for agency personnel to access transition systems in order to centrally control who has what authorities within each system.
	1. Ordering Contracting Officers

The agency’s OCOs, or other officials who have authority to obligate the agency’s funds, are critical to the success of transition, and therefore must be part of the agency’s transition team from the outset. The TOCO, as a key member of the transition team, is the agency’s acquisition lead for facilitating all of the agency’s OCOs’ use of the EIS contracts; this is a role new to the transition to EIS after learning during the transition to Networx the importance of the OCOs’ familiarity with ordering telecommunications services. The TOCO is a critical communication link between GSA and the OCOs within the agency to share best practices for using the EIS contracts, identify OCOs to receive training from GSA regarding ordering from EIS, and access GSA’s acquisition experts for EIS for advice and scope questions.

OCOs are responsible for following the ordering procedures, including the FO selection of contractors in compliance with the FAR, the terms and conditions of the EIS contracts, and any agency policies to place TOs on the EIS contracts. Ordering telecommunications services involves understanding components that are not commonly included in other IT solutions and can require the agency to describe complex network requirements and evaluate disparate proposals or quotations for their solutions. The agency should assign OCOs with experience in telecommunications acquisitions and must ensure the OCOs participate in training that GSA and the EIS contractors offer. GSA has a program to assist agencies with ordering, and agencies can get help by contacting their GSA SB.

For agencies to place TOs on the EIS contracts and to ensure ordering complies with procurement statutes and policies, agencies’ OCOs must attend training and receive a DPA from GSA. DPA Training (FAC066) can be accessed on the Defense Acquisition University website found at https://www.dau.mil/.

* 1. GSA Full Service (Regional Local Services)

All agencies currently using services provided by the GSA Regional local service contracts formerly administered in GSA Regions 1-10 are participating in GSA’s Full Service program. As of October 3, 2017, GSA will not be offering full service on EIS. Agencies participating in the Full Service program need to order their replacement services directly from the EIS contractors.

GSA is committed to supporting agencies throughout this Full Service transition with the assistance to agencies' procurement teams as they make their FO decisions. Agencies that are taking advantage of GSA assistance can include local services in the TO requirements. Agencies may also request GSA's assistance with the Solicitation Assist Tool and EIS Pricer. Agencies that need assistance with analyzing their inventory can request that from GSA; this assistance does not, however, include site surveys. GSA will coordinate with the agencies to ensure all current GSA Regional local services are transitioned to EIS as well as any new requirements. For more information, review the Full Service Transition Plan available online at [gsa.gov/eistransition](http://gsa.gov/eistransition).

# Lessons Learned from Previous Transitions

In report GAO-14-63, *GSA Needs to Share and Prioritize Lessons Learned to Avoid Future Transition Delays*, December 2013, GAO recommended GSA “fully archive, share, and prioritize lessons learned” from the previous transition to Networx. GSA collected lessons learned from previous transitions, predominately from FTS2001 to Networx, and this Transition Handbook addresses many of them, especially those that pertain to agencies’ activities. The complete list of those lessons learned is provided in Appendix C. Furthermore, GSA conducted a comprehensive analysis of the lessons learned. GSA prioritized the lessons and incorporated the significant items into the strategy for NS2020 and transition to EIS; Section 3 of this document reflects those that pertain to transition.

# Transition Planning

As stated in Section 4.1 of this document, each agency must prepare an ATP. The ATP is an important tool for communicating the agency’s requirements, expectations, and approach to other transition stakeholders, including GSA, OMB, and contractors. The ATP must address at least the topics defined in Appendix B – Agency Transition Plan Outline. The Agency Transition Sponsor is to approve and deliver this plan to the TCC at eistcc.ta@gsa.gov within one year after release of the EIS RFP, that is, by October 2016. The TCC will provide it to the GSA’s Assistant Commissioner of FAS/ITC and OMB. GSA will review the ATP and provide feedback to the agency. The ATP will guide the agency’s transition and, therefore, the LTM should update it as needed to remain current and relevant.

Transition planning at the agency level involves identifying key personnel and forming an Integrated Transition Team, confirming inventory, defining requirements and determining the order placement process, and arranging for GSA assistance as needed. The following sections outline these planning activities.

* 1. Identify Key Agency Personnel

The following are key personnel for an agency’s Integrated Transition Team:

* Agency Transition Sponsor
* LTM and supporting TMs
* TOCO and other OCOs for the agency (or personnel with authority to obligate the agency’s funds).

Depending on an agency’s transition requirements, there may be a need to identify additional staff for implementation of transition activities. These resources may come from within an agency or be support contractors and can include financial analysts and billing personnel, local site contacts, information assurance or IT security experts, or network engineers.

* 1. Confirm Inventory

GSA’s role in inventory establishment is to develop, validate, and maintain an accurate Transition Inventory (TI). Building on lessons learned from previous transitions, GSA has conducted the validation of the TI to relieve the agencies of the burden of this labor-intensive and time-consuming task. Validation consisted of a comprehensive comparison of billing and inventory data GSA has collected over the course of the Networx, WITS 3, and GSA Regional local service contracts with that of the contractors on those vehicles. GSA completed TI validation in January 2016 and subsequently provided the TI to the agencies to confirm it is sufficiently complete and accurate for transition planning and tracking. The TI is accessible to authorized agency users through the GSA Enhanced Monthly On-Line Records and Reports of IT Services (E-MORRIS) application. GSA continues to validate and update the TI on a monthly basis as new records are identified, services disconnected, and discrepancies are reconciled.

Confirmation of accurate Networx, WITS 3, and GSA Regional local service inventories ensures agencies and stakeholders have a comprehensive understanding of the services that must be disconnected and provides information for planning for the initial growth of services on EIS. TI confirmation is a critical requirement for a successful transition as identified in the Networx Lessons Learned. An accurate and complete inventory:

* Assists agencies with transition planning by identifying the services to be transitioned and subsequently disconnected from Networx, WITS 3, and GSA Regional local service contracts
* Serves as the database of record for measuring transition progress in a consistent manner across all agencies, contractors, and services
* Serves as an input to the GSA provided on-line site for transition tracking
* Must be confirmed by October 2016; agencies signal completion of the confirmation by asserting such in the ATP.

To further support agencies as they develop their solicitations, and to provide data for transition service orders, the TCC has created a more detailed inventory called the All Agency Inventory (AAI). AAI extends current TI data to a more detailed level, to include individual Contract Line Item Numbers (CLINs), features, equipment, bandwidth, and other data not currently included in TI. The data is primarily based on contractor inventory, billing, and orders for Networx, WITS 3, and Regional local service contracts. Output of this data is available upon a request to the TCC through the SB. The TCC offers agency-level detail records and several different reports summarizing the data in a myriad of ways for agency use and dissemination. The normalization and consistency of data used for ordering should result in faster ordering from the FO process to provisioning, and implementation to billing verification.

* 1. Define Requirements and Order Placement Process

EIS service requirements are driven by agency-specific mission needs and operational models. Requirements for EIS ordering should be determined by conducting a complete analysis of an agency’s current inventory of telecommunications services and its future operational needs. The agency should carefully consider how to approach enterprise transformations or network optimizations; it may be more effective to address these complex projects as part of normal network management and not assume they have to be done during transition. Conversely, if the agency’s requirements are well developed and funded, transition may be the best time to complete these projects. With those requirements in mind, the agency should become familiar with the appropriate requirements in the EIS contracts, paying particular attention to performance specifications for services in Section C, management and operations requirements in Section G, service level agreements, and deliverables. This analysis will determine how the EIS service offerings can best meet an agency’s needs. Requirements can then be grouped into one or more FO solicitations, and a contractor can be selected through the process in compliance with FAR 16.505 to meet the agency’s requirements.

***Define Requirements***

Contact your SB for assistance with writing a solicitation.

The steps for defining requirements and determining the order placement process include:

* Determine and document requirements
* Conduct market research
* Develop acquisition plan (inclusive of the Independent Government Cost Estimate, or IGCE)
* Reference FAR 16.505; requirements differ based on the dollar thresholds.
* Decide how many solicitations are appropriate and develop them. Each solicitation can result in one or more TOs upon selection of the contractor(s)
* Determine order placement process to be used in compliance with FAR 16.505 and in accordance with the terms and conditions of the contract
* Conduct fair opportunity, as required and according to the defined order placement processes
* Award a TO(s) based on the results of the FO process; TO(s) must be fully funded
* Place service orders against TO(s), including reference back to the TO(s).

GSA has published a Fair Opportunity and Ordering Guide for additional guidance (see gsa.gov/eistransition).

* 1. Arrange for GSA Assistance
		1. GSA-Assisted Transition

For agencies that have very straight-forward transitions with limited staff to conduct the transition, GSA can assist with the FO process and placing orders. An example of a transition that could meet this requirement is a smaller agency with only voice services and basic internet connectivity requirements through Networx; although, other types of services could also qualify. The agency will execute an IAA with GSA that specifies the type and level of support, such as price comparison reports or assistance with using GSA’s Solicitation Assist Tool or assistance with executing TOs on EIS. GSA will contact agencies that are candidates for this assistance, or agencies may inquire through their SB.

* + 1. Transition Assistance

For agencies not in the GSA-Assisted Transition program, GSA offers assistance in other forms. While each agency is responsible for its own transition to EIS, agencies may request GSA’s assistance with transition activities. For example, help is available for the following:

* Inventory Confirmation
* Solicitation Development
* Pricing Research
* Transition Planning
* Training
* Price and Technical Evaluation
* Ordering Process
* Cutover Guidance
* Disconnect Assistance
* Transition Complete Verification
* Transition Risk Assessment (from September 2021 through March 2022).

GSA provides assistance tailored to each agency’s needs, and agencies can request assistance as needed as well as receive dedicated assistance. GSA can help agencies through the FO process and ordering services from the EIS contract, including analyzing customer requirements, proposing solutions and assessing their feasibility, making recommendations for service selection, determining the cost of the services, selecting an EIS contractor, and guiding customers on placing orders for those services.

Dedicated assistance for transition ordering is in the form of third-party contractor support. The TCC funded the TOA TO through September 2021 under a GSA contract to provide direct contractor support. Similar support is also available to agencies through the TCC. In addition, network engineering assistance for implementation of complex TOs is available to agencies through the Transition Engineering Assistance (TEA) project.

An agency can request assistance by contacting its SB at GSA and should certainly consider it while developing the ATP and include any requirements in that plan when delivering it to GSA prior to the EIS award. The assistance offered by GSA is available to the agencies for a specific set of requirements, on a reimbursable basis, and is not meant to augment an agency’s staff or perform inherently government functions. GSA and each agency receiving services from the TO establish an IAA. GSA retains overall TO administration, project management, funding, and performance-monitoring responsibilities for this task; the agency supports GSA by identifying in the IAA a project manager (PM) at the agency who will monitor the contractor's performance, including deliverables, and report quarterly to the TO Contracting Officer’s Representative (COR). The PM also integrates the consultant contractors into the procurement team conducting the FO activities, including the OCO, as well as financial, program office, and technical experts.

* + 1. GSA TCC Training Plan

The GSA TCC Training Plan for EIS consists of courses designed to assist agencies with the transition to EIS. Training modules are available through Instructor Led Training (ILT) and eLearning modules. Additional information and access to previously recorded training sessions can be found at [www.gsa.gov/eistransition](http://www.gsa.gov/eistransition).

Training modules include the following topics:

* EIS Fundamentals (Archived July 2017)
* Transition Inventory (TI)
* All Agency Inventory (AAI)
* Telecom 101 and EIS Pricing Structures
* EIS Pricer
* Solicitation Assist Tool
* Fair Opportunity and Ordering
* Delegation of Procurement Authority
* Introduction to GSA Conexus
* EIS Management and Operations.

# Transition Management and Implementation

GSA’s FOOG provides more detailed guidance on the process, and the MOPS Handbook explains the ordering and billing requirements in the EIS contracts ([gsa.gov/eistransition](http://gsa.gov/eistransition)). The summary information below can assist with planning.

* 1. Develop Fair Opportunity Solicitations

When developing FO solicitations, agencies should be mindful of factors that can facilitate or expedite the TO award process and result in the best solution at the best price. Variations are certainly allowable but may increase the time for contractors to develop proposed solutions and can increase cost. These factors include:

* Minimizing customized service level agreements or billing requirements beyond those specified in the EIS contracts
* Providing detail to describe requirements more comprehensively, for example, including the TI for services to be replaced
* Describing requirements functionally rather than as pre-defined technical solutions or specific products
* Using pricing templates structured similarly to those in the EIS contracts.
	1. Award Task Orders

Through the order placement process for each set of requirements, the agency’s OCO will select the EIS contractor best suited to provide the required services and execute a TO with the contractor. The OCO must obligate sufficient funds on the TO to cover the base period. Agencies may elect to place service orders. If elected, service orders must be within scope of the TO and EIS contract, and cannot obligate funds or exceed the established funding on the TO. The funding obligation on the TO may be a not-to-exceed (NTE) amount. Subsequently, the agency may begin placing service orders against the TO following the process described below in Section 8.3, Ordering Process.

* 1. Ordering Process

Once the TO has been awarded, the agency orders service directly from the selected EIS contractor, within the scope, prices, ceiling value, and terms and conditions of the OCO-awarded TO. The TO must identify the OCOs and CORs who have authority to order services. The selected EIS contractor may consult with the agency to expedite the ordering process and to provide the tools needed to ensure that all orders are properly placed. The EIS contractors may also provide training to the agency on placing orders for their services.

During the ordering process, agencies should be mindful of lessons learned from previous transitions:

* Do not assume a back office transition will be easier than changing contractors or will not be service-affecting; many of the same transition activities still need to be completed
* If a selected solution requires the contractor to modify the EIS contract, that modification will take time
* Replacing equipment requires close coordination to ensure the new equipment is available and acceptable so as not to introduce delays
* Different contractors and service providers may use different physical addresses for the demarcation of service delivery; the agency may have to provide the address as well as LAT/LONG coordinates and ensure the contractor is able to identify the correct demarcation prior to dispatching to the location.
	1. Service Implementation

Delays in service implementation can be reduced by incorporating the following lessons learned:

* Before approving an implementation plan or site survey, ensure services meet the agency’s technical and operational requirements; for example, all 800 numbers should be included in the site survey
* Advise contractor of any special access requirements for the site
* Make arrangements for the contractor’s technicians to access the site and avoid unnecessary ‘turn-aways’
* Ensure local contacts understand the plan for their site including the type of cutover (parallel, managed, or coordinated) planned
* Have material/equipment installed and ready on scheduled cutover date (for example cabling, inside wiring, Private Branch Exchange (PBX) cards, or other Government Furnished Equipment (GFE)
* Have needed technicians and local vendors—such as PBX vendors—on hand for both pre-test and cutover.

Reference Appendix G for cutover guidance to assist with planning the transition of services to EIS.

* 1. Transition Tracking and Reporting

GSA tracks transition across the government and reports the progress of activities to ensure transition occurs on schedule. GSA’s TCC uses tracking data to analyze trends to identify problems with a specific contractor, a certain service, or an agency in need of transition assistance and to formulate resolutions proactively. Tracking and reporting EIS transition status enables the EIS PMO, GSA senior management, agencies, and the contractors to forecast the complexity and duration of transition for financial and human resource planning. It also allows decision-makers to track progress against the impending expiration of the Networx, WITS 3, and GSA Regional local service contracts and take action if needed.

GSA’s tracking of EIS transition progress employs three methods of data collection and analysis:

* Record agency decisions and plans that indicate an agency’s readiness for transition
* Measure the extent to which services are being implemented on EIS contracts and are being disconnected from expiring Networx, WITS 3, and GSA Regional local service contracts
* Inspect reports to identify major or chronic issues or negative trends.

Measures and tools to track transition progress have been developed and will be refined as needed. They currently include measures of the rate of disconnected services from Networx, WITS 3 and Regional local service contracts as well as the growth of business on the EIS contracts. See Appendix D for a sample dashboard report for large and medium agencies.

* 1. Stakeholder Communications for Transition

Communications with stakeholders play a critical role in the successful transition of an agency’s telecommunications services. Several methods of communication have been established to assist agencies with communications throughout transition. These methods include:

* Infrastructure Advisory Group (IAG)
* Help Desk
* EIS Transition websites
* EIS Bulletins.
	+ 1. Infrastructure Advisory Group

The IAG provides guidance to GSA on its IT and telecommunications programs. It assists with developing a consensus on common issues that affect multiple agencies; as such it will attend to the development of new GSA contracts. The IAG promotes collective government planning related to the transition to the EIS contracts.

* + 1. Help Desk

GSA’s IT Customer Service Center (ITCSC) is available to agency customers and contractors to help resolve issues and questions regarding transition. The ITCSC does not replace the EIS, Networx, WITS 3, or GSA Regional local service contractors’ customer service or trouble management services. It is primarily a means for contacting the TCC and the GSA program team. Agencies can reach the ITCSC by phone at 855-482-4348 or by email at itcsc@gsa.gov.

***Help Desk***

For assistance, contact your SB (gsa.gov/nspsupport) or the IT Customer Service Center (855) 482-4348, ITCSC@gsa.gov

* + 1. EIS Transition Website

The TCC stood up the EIS Transition website to communicate activities specific to transition at [gsa.gov/eistransition](http://www.gsa.gov/portal/category/101134) and continues to manage this website within the GSA web infrastructure to support the transition to EIS. The transition website provides transition guidance to federal agency customers and shares transition status with the agencies and the general public. Tools on the website include a wide variety of support documents such as planning documents and guides; transition training courses, such as Instructor Led Trainings (ILTs), self-paced eLearning, and recorded training sessions; Frequently Asked Questions (FAQs) and other basic resources; and, as appropriate, data on transition status. Updates on EIS and a link to the EIS Transition website are also available on[gsa.gov/eis](http://www.gsa.gov/portal/content/219379)**.**

* + 1. EIS Bulletins

The TCC periodically publishes EIS Bulletins with transition related topics for consideration by agencies, EIS contractors, and GSA. Topics are based upon feedback received through several forums. Bulletins follow a simplified, but thorough, approval process to facilitate timely communication of information to stakeholders.

* 1. Disconnects

Disconnecting an agency’s Networx, WITS 3, or GSA Regional local services is the last milestone in transition to EIS. For every EIS transition order there should be one or more corresponding Networx, WITS 3, or GSA Regional local service disconnect orders. Coordinated and synchronized disconnects and activation by different service providers are essential to ensure transition success. The TI also reflects Networx, WITS 3, and GSA Regional local service disconnects for services moved to other contract vehicles or disconnected and not replaced.

***Disconnects***

For more information concerning disconnecting Networx, WITS 3, or GSA Regional local services, please see the redacted contracts for your contractor.

# Summary

Telecommunications services must transition from expiring Networx, WITS 3 and GSA Regional local service contracts. GSA provides guidelines and direct assistance to agencies on managing the transition of their services to EIS contracts. Agencies can request additional information on transitioning Networx, WITS 3 and GSA Regional local services to EIS from their GSA SB or by contacting the ITCSC.

***Contact Us***

For more information on Networx, NS2020, or EIS, please contact your SB (gsa.gov/nspsupport) or the IT Customer Service Center (855) 482-4348, ITCSC@gsa.gov.

# Appendix A – Acronym List

|  |  |
| --- | --- |
| AAI | All Agency Inventory |
| AB Code | Agency Bureau Code |
| AHC  | Agency Hierarchy Code |
| ARS | Automatic Route Selection |
| ATP | Agency Transition Plan |
| BOT | Back Office Transition |
| CIO | Chief Information Officer |
| CLEC | Competitive Local Exchange Carrier |
| CLIN | Contract Line Item Number |
| COR | Contracting Officer’s Representative |
| CoS | Continuity of Service |
| DPA | Delegation of Procurement Authority |
| EIS | Enterprise Infrastructure Solutions |
| eLearning | Electronic (computer based) Learning |
| E-MORRIS | Enhanced Monthly On-Line Records and Reports of IT Services |
| FAR | Federal Acquisition Regulation |
| FAS | Federal Acquisition Service |
| FAQ | Frequently Asked Questions |
| FO | Fair Opportunity |
| FY | Fiscal Year |
| GAO | Government Accountability Office |
| GFE | Government Furnished Equipment |
| GSA | General Services Administration |
| HVAC | Heating, Ventilating, and Air-Conditioning |
| IAA | Interagency Agreement |
| IAG | Infrastructure Advisory Group |
| ICB | Individual Case Basis |
| IGCE | Independent Government Cost Estimate |
| ILEC | Incumbent Local Exchange Carrier |
| ILT | Instructor Led Training |
| IP | Internet Protocol |
| IT | Information Technology |
| ITC | Information Technology Category |
| ITCSC | Information Technology Customer Service Center |
| LEC | Local Exchange Carrier |
| LL | Lessons Learned |
| LTM | Lead Transition Manager |
| MACD | Move, Add, Change, Disconnect |
| MOPS | Management and Operations |
| NAUL | Networks Authorized User List |
| NS2020 | Network Services 2020 |
| NTE | Not-to-exceed |
| OCO | Ordering Contracting Officer |
| OMB | Office of Management and Budget |
| OTS | GSA’s Office of Telecommunications Services |
| PBX | Private Branch Exchange |
| PIC | Primary Interexchange Carrier |
| PMO | Program Management Office |
| RFP | Request for Proposal |
| RFQ | Request for Quote |
| SB | Solutions Broker |
| SOP | Standard Operating Procedure |
| SOW | Statement of Work |
| TBD | To be determined |
| TCC | Transition Coordination Center |
| TEA | Transition Engineering Assistance |
| TI | Transition Inventory |
| TM | Transition Manager |
| TO | Task Order |
| TOA | Transition Ordering Assistance |
| TOCO | Transition Ordering Contracting Officer |
| TOPS | Telecommunications Ordering and Pricing System |
| VLAN | Virtual Local Area Network |
| WITS 3 | Washington Interagency Telecommunications System 3 |

# Appendix B – Agency Transition Plan Outline

**B.1** **Project Scope and Charter**

Describe the business needs, current understanding of needs of users across the agency, and services the project is intended to provide. Include the following areas:

* Purpose or justification
* Measurable objectives and success criteria
* High-level requirements
* High-level risks
* Summary milestone schedule
* Summary budget.

**B.2** **Leads for Integrated Transition Team**

Identify names and contact information for the following roles:

***B.2.1*** ***Agency Transition Sponsor***

Chief Information Officer (CIO) (or other) Senior Executive Service Sponsor – Lessons learned from previous transition have highlighted the need for an executive level manager that sponsors the agency’s transition project. The sponsor likely would be the CIO or executive of the organization to which the transition manager and team report or that otherwise provides the financial and human resources for the transition. The sponsor serves as a spokesperson to higher levels of management, is the primary interface and partner to GSA executives, and is the agency’s representative accountable to oversight organizations. Important activities for the Agency Transition Sponsor include approving the agency’s Transition Plan and serving as an escalation path.

***B.2.2*** ***Lead Transition Manager***

Each agency should have a Lead Transition Manager (LTM) and may also designate other supporting transition managers (TMs). The LTM acts as the central point of contact for the planning, management, and implementation of the agency’s transition of services from Networx, WITS 3 and GSA Regional local service contracts to EIS.

***B.2.3*** ***Transition Ordering Contracting Officer***

The agency’s Transition Ordering Contracting Officers (TOCOs) are critical to the success of transition and, therefore, must be part of the agency’s transition team from the outset. The TOCO is the agency’s lead for facilitating the use of the EIS contracts. TOCOs are responsible for following the ordering procedures, including the FO selection of contractors, in compliance with the Federal Acquisition Regulation (FAR) 16.505, the terms and conditions of the EIS contracts, and any agency policies to place task orders (TOs) on the EIS contracts. The agency should assign TOCOs with experience in telecommunications acquisitions and must ensure the TOCOs completes and receives certification in GSA’s Delegation of Procurement Authority (DPA) training.

***B.2.4*** ***Escalation Path to Agency Transition Sponsor***

List the management structure (names, roles, and contact information) that links the LTM and TOCO to the Agency Transition Sponsor.

**B.3** **Support Organization**

***B.3.1*** ***Integrated Transition Team Members***

Describe the other organizational functions within the agency that will participate in transition planning and execution, such as supporting TMs, financial analysts and billing personnel, local site contacts, information assurance or IT security experts, or network engineers.

***B.3.2*** ***Support Contractors***

Agencies may require contractor support to assist in the following areas:

* Inventory information gathering
* Inventory validation
* Transition Plan writing or review of vendor agency transition planning documents
* Technical assistance in assuring that services are ordered to replace existing services
* Defining requirements and selecting contractors through the FO process
* Order writing: both installation orders and disconnect orders
* Technical assistance at the time of transition to assist in problem resolution
* Site surveys to assure that agency facilities are ready for vendor installation of services and equipment
* Transition scheduling and transition tracking.

***B.3.3*** ***AHC Structure***

Identify what AHCs fall under the authority or scope of the agency for transition.

**B.4** **Strategy**

***B.4.1*** ***Agency priorities and objectives during transition***

* Like for like, transformations, enhancements
* Competing or complementary activities
* Verification and testing

***B.4.2*** ***FO Decisions***

* Approach for solicitations to select EIS contractor(s); describe the scope of requirements to be grouped into each solicitation, quantity of solicitations and expected resulting task order(s), evaluation criteria, staff quantity and skill level of source selection team
* Requested GSA assistance, such as: acquisition support, GSA-assisted transition, training, or self-help with GSA guidance.

***B.4.3*** ***Schedule***

Include milestones from master schedule and additional detail of activities. Include expected release and award dates for each FO decision.

**B.5** **Inventory Analysis**

***B.5.1*** ***Summary by service type, quantities, locations***

***B.5.2*** ***Equipment condition***

***B.5.3*** ***Confirmation status***

**B.6** **Mission Analysis**

***B.6.1*** ***Constraints***

Discuss moratoriums, blackout or quiet periods, planned projects affecting transition, and new mission plans.

***B.6.2*** ***Risks***

***B.6.3*** ***Jeopardies***

Appendix C – List of FTS2001 to Networx Lessons Learned

|  |  |
| --- | --- |
| **LL #** | **Lesson** |
| 1 | The replacement of the telecommunications infrastructure for a large part of the federal community is a huge task. The transition stakeholders (that is GSA, the user Agencies and the gaining service providers) need to be fully prepared for the undertaking.  |
| 2 | A funding mechanism like the Transition Fund is strongly recommended for any future transition efforts similar to FTS2001.  |
| 3 | To make Agency resource planning easier, it is recommended that guidelines based on the “Taxonomy” document be established early enough in the budget cycle for Agencies to do the financial planning required to ensure that needed resources are available.  |
| 4 | The reimbursement plan between GSA and the Agencies should be based on clear financial criteria that result in predictable Agency impact. |
| 5 | A complete and accurate “baseline” inventory prior to contract award is critical. In order to facilitate this requirement it is suggested that inventory validation should be an on-going effort during the life of the contract to provide a complete and accurate baseline for not only transition, but also other operations such as billing validation and service optimization. |
| 6 | The roles and responsibilities of all transition stakeholders (that is GSA, Agencies, and service providers) should be clearly defined and communicated to ensure critical activities are appropriately performed. |
| 7 | Many Government requirements cannot be met by standard Commercial services. Although commercial solutions are encouraged, solicitation documents and all planning must include Government unique requirements. |
| 8 | Agencies should be prepared for the ‘worse-case’ scenario of their current service provider either not being awarded a successor contract or not being selected through the fair opportunity process and plan accordingly in order to ensure a rapid transition effort with minimal impact on the continuity of service. |
| 9 | A “one size fits all” approach to program management must be avoided since Agency capabilities differ widely. For each Agency will likely not have the same transition experience. At the same time, the approach must ensure that the needs of all Agencies, large and small, are being addressed. The approach either needs to ensure that resources are available when the plan requires or that the plan can be tailored to fit the available resources |
| 10 | Agencies should anticipate and account for the new service provider’s possible inability or unwillingness to execute all transition requirements as expected thus ensuring that they (a) Establish and maintain effective oversight throughout transition and escalate problems with the service providers to GSA with documentation, and (b) GSA should anticipate and be prepared to deal with service provider’s possible inability or unwillingness to meet contractual obligations. |
| 11 | Overall transition planning should have sufficient flexibility so that Agencies can coordinate transition with other ongoing activities regardless of the impact of external events. Likewise, contracts should be flexible to accommodate unforeseen marketplace issues. |
| 12 | Coordinated and synchronized disconnects and activation by different service providers are essential to ensure transition success. |
| 13 | Agencies should consider whether network optimization would be more effectively addressed as part of normal network management or during transition. |
| 14 | The planning activities of the transition stakeholders (that is GSA, Agencies, and service providers) should be coordinated to ensure all activities are appropriately accounted for and that dependencies are adequately addressed. |
| 15 | The task of transition is not limited to transitioning a static list of services on a like-for-like basis. Therefore, Agencies should anticipate the need for changing connectivity during the transition effort and mitigate those factors in their transition plan(s). |
| 16 | Care should be exercised when determining the MRGs to be offered to ensure that (a) They do not become an impediment to Agency choice and competition in the future, (b) They do not become a disincentive to winning contractors to aggressively move forward; In short, MRGs should be managed so as not to impede the transition effort. |
| 17 | The delay in Agencies selecting their vendors significantly impacted the timeline for transition. Therefore, a “deadline” for vendor selection should be incorporated into the overall transition schedule.  |
| 18 | Agency procedures and resources were inadequate to manage the extraordinary volume of service orders associated with the transition effort. |
| 19 | Agencies responsible for slow contractor selection, transition planning and/or order entry that directly results in extension of incumbent contract(s) and services should bear the costs associated with those extensions. |
| 20 | In any future efforts, service providers should be held to the required levels of service from contract award (including the transition period). |
| 21 | Agencies should ensure their plans accommodate for potential issues associated with access facilities, as often service providers do not control the entire provisioning process. |
| 22 | Service providers need to apply sufficient, properly trained resources in order to meet the identified transition goals. |
| 23 | Future transition planning should not permit transition to begin until service provider support systems are in-place, tested, and accepted. Further, service providers should be required to deliver support systems for both Commercial and Government unique services that meet Government expectation prior to contract award. |
| 24 | Some delays could be avoided if Agencies (a) Take care not to approve a TPSP or site survey if services are not in fact what they need to operate (e.g. all 800 numbers were not included in site survey); (b) Advise service provider of any special access requirements for the site, (c) Make arrangements for the entry of service provider technicians into site in order to avoid unnecessary ‘turn a-ways’; (d) Ensure that they know and understand the plan for their site including the type of cutover (parallel, managed, or coordinated) planned; (e) Have material/equipment installed and ready on scheduled cutover date (e.g. cabling, inside wiring, PBX cards, or other GFE equipment); (f) Have needed technicians on hand for both pre-test and cutover (e.g. PBX technician was not present on scheduled test dates resulting in dialing plan problems). |
| 25 | GSA and Agencies should proactively examine invoices during transition to verify that services are being invoiced against the right contract and the right rate and that the details of billing meet contract requirements. Also, billing discrepancies should be brought to the attention of service providers promptly and GSA must hold them responsible for resolving billing problems expeditiously. |
| 26 | The progress of transition should be measured by both the “old” services replaced and disconnected as well as by the “new” services installed. |
| 27 | Government should specify the information required from the service providers relative to transition progress as opposed to the method by which it is delivered. Further, how information is captured and presented by the service provider and GSA needs to be carefully documented for the Agencies and the Agencies need to be flexible as to how they can manipulate and use this data. |
| 28 | Effective and consistent transition metrics should be established and agreed upon by all transition stakeholders prior to contract award. |
| 29 | GSA will encourage participation from customer Agencies so that they are intimately familiar and comfortable with the structure of the contracts well before they are awarded. This will help reduce the learning curve after award. |
| 30 | Contractor ordering processes need to be integrated with TOPS (or replacement) ordering processes. |
| 31 | Require secure FTP servers be operational at award. |
| 32 | Redefine the period for measuring the intervals. |
| 33 | Include requirement in solicitation for toll free number to allow users to verify they are on the selected contract. |
| 34 | If CSDS still exists, combine requirements for voice services and CSDS. |
| 35 | Investigate Ways to Improve the Timeliness of Fair Opportunity Decisions |
| 36 | Separate intervals for switched and dedicated access, calling cards. |
| 37 | Require Caller ID to include a name. |
| 38 | Require contractors to accept bulk order disconnects. |
| 39 | Provide a solution for Agencies to see their inventories behind GSA Systems. |
| 40 | Define transition reimbursement requirements and process in advance of RFP and include requirements to accommodate the process. |
| 41 | The ability for agencies to buy comprehensive network solutions from a single source (GSA) should remain an important one in planning for NS2020 |
| 42 | Contracts should have broad enough scopes to account for changes in technology and pricing methods |
| 43 | The range of OTS Regional Offices services offered should be broadened in order to better fulfill customers’ needs and to move on from the current business model |
| 44 | The NS2020 portfolio of service offerings should facilitate customers’ adoption of emerging technology trends, such as the proliferation of cloud services and wireless network access |
| 45 | Enable access to solutions through the entire ITS portfolio of services and capabilities |
| 46 | Establish an integrated portfolio of contract vehicles to serve the full range of agency needs |
| 47 | Establish complementary contracts matching agency buying patterns to market segments |
| 48 | Ultimately, both the National and Regional Office programs must ensure that future contracts and support services satisfy agency mission requirements with excellent value. The OTS national and regional offices should cooperatively plan the future program portfolio that addresses the variable needs of agency headquarters and field units using an appropriate mix of national and regional contracts. |
| 49 | Agencies should engage Agency COs in the beginning of the transition process. Suggest creating Agency Tiger Teams (with key stakeholders) for appropriate dissemination of pertinent transition related information. |
| 50 | Build lead/lag time into the transition plan to accommodate time for contract modifications. |
| 51 | Capture Local Government Contact (LGC) information from order to Service Order Completion Notice (SOCN) then to inventory. |
| 52 | Develop measurement standard for the inventory and determine inventory elements. |
| 53 | Transition Inventory (TI) should include a requirement to be updated when new or replacement circuit IDs are introduced. |
| 54 | When adding or modifying a service or contractual requirement, consideration should be given to what impact it will have on the process for reimbursing transition costs. |
| 55 | GSA’s stakeholder outreach efforts should be extended and strengthened to increase the early involvement and buy-in of higher-level Federal managers such as CIOs and their immediate representatives, as well as OMB’s Resource Management Office (RMO) and Office of E-Government & Information Technology. |
| 56 | Any structural disincentives to collaboration, such as variable revenue recognition across OTS contracts, should be identified and addressed. |
| 57 | Proper incentives for OTS national and regional programs to work together should be formalized. This includes regions working with each other. |
| 58 | GSA should strive for more effective collaboration among OTS program staff and COs, as well as more effective coordination with external stakeholders. |
| 59 | Transition Managers should be associated with AB Codes. |
| 60 | GSA should provide expanded outreach support for smaller agencies to focus and address specific transition needs and options. Provide follow-up support for preparing and completing fair opportunity decisions and support tool training. |
| 61 | Maintain Agency TM information and status throughout contract lifecycle. Accurate and current agency contact information will enable GSA to coordinate planning, communication, and outreach for the next transition. |
| 62 | Explore other incentives, in addition to Transition Reimbursement, to provide sufficient motivation for agencies to execute their fair opportunity decisions and transition. |
| 63 | Voice service PICed to service provider prior to SOCN, resulting in commercial billing. This Impacts “transition” and "new" service orders. Need flexibility to allow IXC to re-rate charges, or to prevent PIC from occurring prior to SOCN. |
| 64 | Dedicate trained personnel to handle disconnects. |
| 65 | Do not assume that a back office transition will be easier than change of provider. Many of the same transition elements still need to be coordinated with a back office transition. |
| 66 | Centralize ordering system process but decentralize ordering. |
| 67 | Provide drop down list of valid values for Agencies to select from when documenting fair opportunity decisions. |
| 68 | Revisit the Definition of Billing SLAs |
| 69 | Clear definition of account ownership – who is the directly responsible individual – for each account’s satisfaction should be defined. |
| 70 | GSA should provide a means for agencies to obtain third party acquisition assistance either directly through the OTS or through a partnership between OTS and other GSA service. |
| 71 | GSA should anticipate customers to want more extensive and continuous support from OTS for complex FO decisions. |
| 72 | GSA should establish an outreach and governance model that recognizes the perspectives of finance, acquisition, and information technology, and promotes coordination between senior executives in these organizations. |
| 73 | Equipment replacement actions were inaccurate and took an excessive amount of time |
| 74 | Back office transition (BOT) process' were not rapid, efficient and non-service-affecting |
| 75 | Numerous CLINs that were amended or changed on an order did not receive transition credit |
| 76 | Agencies need to get a copy of the vendors' inventory files that will allow them to do a better job of reconciling inventory |
| 77 | Multiple and repetitive reconciliations of TOPS inventory as a result of not being centrally managed |
| 78 | Inventory problems (1) Baseline and (2) complexity of reconciliation and validation with agencies, vendors and Local Exchange Carriers (LECs) |
| 79 | Innovative approaches to minimize the FO impact to agency customers should be sought. Examples of approaches to be considered include GSA making some FO decisions during initial contract award and offering pre-awarded, “turn-key” services, which would be similar to many current regional operations. |
| 80 | GSA should anticipate agency customers to increasingly require OTS to (a) Provide significant support to facilitate transitions, and/or (b) Structure the contracts and transition processes to ease agency workloads |
| 81 | OTS should propose the integration of the IMC into the Federal Chief Information Officer Council (CIOC), given the similar missions and synergies of the two governance boards. This will ensure top-level attention to infrastructure activities. |
| 82 | Contractor's ordering and invoicing processes and systems have an impact on the success of the TCR process. |
| 83 | Agency COs should meet with GSA’s Program COs for and advice and scope determinations questions. |
| 84 | Agencies should consider the effectiveness of separating Wide Area Network (WAN) decision from other systems. |
| 85 | Identity contract modifications for inside wiring, since most inside wiring is ICB on FTS2001 and Networx. |
| 86 | Separate TIC solution Fair Opportunities from Transition Fair Opportunity decisions. |
| 87 | Agency should conduct Requests for Information (RFI) when writing their SOW. |
| 88 | Complete decisions on definitized CLINS first before the other decisions needed for the Agency. |
| 89 | Agencies need a vendor supplied website that will provide a physical address for all data Networx services for validation of demark or service addresses |
| 90 | Improve usability and interface of GSA's Networx Unit Pricer |
| 91 | Make Lessons Learned, FAQs and Knowledge Base readily available to Agencies. |
| 92 | Agencies should continuously and regularly validate their inventory throughout the Networx contract-monthly if possible. |
| 93 | Networx Pricer needs mechanism for pricing current inventory. |
| 94 | Vendor OSS/notifications were unreliable and need to be sent in accordance with GSA established SLAs |
| 95 | The regional business model, including service offerings, should be adjusted to account for changes in technology. |
| 96 | GSA should provide more proactive OTS responses to unexpected issues as they arise, before they result in significant negative consequences. |

Appendix D – Sample Dashboard Reports for Large and Medium Agencies’ Transition Progress

Large Agencies



Medium Agencies



Appendix E – Agency Transition Checklist

| **Agency Checklist Actions** | **Additional Details** |[x]  **Target Date** |
| --- | --- | --- |
| Identify transition points of contact | Agency Transition Sponsor |[ ]  May 2016 |
|  | Transition Ordering Contracting Officer (TOCO) |  |  |
|  | Lead Transition Manager (LTM) |  |  |
| Identify and contact GSA Solutions Broker (SB)  | [gsa.gov/nspsupport](https://www.gsa.gov/portal/content/103828) |[ ]  May 2016 |
| Receive IAA TAP transition briefing | Coordinated by GSA SB |[ ]  May 2016 |
| Complete draft IAA | Indicates intent to use GSA provided consultant support |[ ]  May 2016 |
| Request access to GSA Tools | 1. Transition Inventory Access: see Transition Inventory User Guide (gsa.gov/eistransition)
 | [ ]  | Oct 2016 |
|  | 1. Conexus – EIS Ordering, Billing, and Inventory Functionality (conexus.gsa.gov)
 |  |  |
|  | 1. Subscribe to Interact for real-time notifications of EIS and transition activities (interact.gsa.gov/eis)
 |  |  |
| Review and confirm agency’s transition inventory | 1. Identify who will review and confirm agency inventory
 | [ ]  | Oct 2016 |
|  | 1. Download agency inventory from TI
 |  |  |
|  | 1. Review inventory
 |  |  |
|  | 1. Identify discrepancies
 |  |  |
|  | 1. Communicate discrepancies through TI application
 |  |  |
| Review EIS RFP to become familiar with the available services, management and operations requirements, and pricing structure | SAM.gov; Ref. Solicitation No. QTA0015THA3003 |[ ]  Oct 2016 |
| Take available training courses (Ref. EIS Training Opportunities on [gsa.gov/eis](http://www.gsa.gov/portal/content/219379)) | 1. EIS Fundamentals (Archived July 2017)
 |[ ]  Jun 2016 – Post EIS Award |
|  | 1. Transition Inventory
 |  |  |
|  | 1. All Agency Inventory Modules I-III
 |  |  |
|  | 1. Fair Opportunity and Ordering Guide
 |  |  |
|  | 1. Management and Operations
 |  |  |
|  | 1. EIS Pricer
 |  |  |
|  | 1. Introduction to GSA Conexus
 |  |  |
|  | 1. Telecom 101 and EIS Pricing and Structures
 |  |  |
|  | 1. Delegation of Procurement Authority
 |  |  |
|  | 1. Solicitation Assist Tool
 |  |  |
| Develop Agency Transition Plan (ATP) | 1. Department level
 |[ ]  Oct 2016 (initial) update as appropriate |
|  | 1. Determine number of Fair Opportunity (FO) decisions and expected release dates and task order award dates
 |  |  |
|  | 1. Define transition budget plan, dependencies, risks
 |  |  |
|  | 1. State that inventory has been confirmed
 |  |  |
|  | 1. Estimate human resource requirements and coordinate with agency staffing and training plans for FY 2016-2023
 |  |  |
|  | 1. Complete ATP worksheet
 |  |  |
|  | 1. Submit ATP and worksheet to eistcc.ta@gsa.gov mailbox
 |  |  |
| Finalize IAA for GSA consultant support | 1. Identify agency IAA signatory
 |[ ]  As contacted by GSA |
|  | 1. Identify a PM to monitor consultant’s performance
 |  |  |
|  | 1. Communicate number of FOs and type
 |  |  |
|  | * 1. Complex: RFP, SOW
 |  |  |
|  | * 1. Simple: RFQ, Price Only
 |  |  |
|  | 1. Identify consultant clearance requirements (as applicable)
 |  |  |
|  | 1. Finalize resource allocation needs and timing
 |  |  |
|  | 1. Conduct kick-off meeting with GSA consultants
 |  |  |
|  | * 1. Agency LTM, TOCO, and OCO for each FO Decision
 |  |  |
|  | * 1. GSA SB
 |  |  |
|  | * 1. Consultant support
 |  |  |
|  | * 1. TCC
 |  |  |
|  | 1. Participate in Quarterly IAA reviews (recurring)
 |  |  |
| Agency OCOs receive Delegation of Procurement Authority | 1. Identify the OCO for each FO Decision
 |[ ]  Aug 2017 |
|  | 1. Each OCO completes DPA training on DAU (FAC066)
 |  |  |
|  | 1. Request DPA using Request Form (hyperlink to form available on www.gsa.gov/eis)
 |  |  |
|  | 1. Email EIS DPA training completion certificate to EIS\_DPA@gsa.gov
 |  |  |
|  | 1. Receive official DPA letter from GSA EIS CO authorizing OCO to issue task orders on EIS
 |  |  |
| Develop FO solicitations (see Fair Opportunity and Ordering Guide on gsa.gov/eistransition) | 1. Develop schedule for completing FOs
 |[ ]  Jan 2017–Jul 2017 |
|  | 1. Define Service Requirements
 |  |  |
|  | * 1. Define Service Groups
 |  |  |
|  | * 1. Document requirements within a SOW, PWS, or SOO
 |  |  |
|  | 1. Develop Acquisition Strategy
 |  |  |
|  | * 1. Select Acquisition Strategy
 |  |  |
|  | * + 1. Price-only
 |  |  |
|  | * + 1. Low Price Technically Acceptable (LPTA)
 |  |  |
|  | * + 1. Best Value Tradeoff
 |  |  |
|  | * 1. Prepare Acquisition Plan
 |  |  |
|  | 1. Draft Solicitation and the complete Acquisition Package (driven by acquisition method)
 |  |  |
|  | * 1. Map Agency Service Locations to Core Based Statistical Areas (CBSAs)
 |  |  |
|  | * 1. Add Service Inventory as an attachment to SOW/PWS/SOO
 |  |  |
| Update draft solicitation to reflect changes consistent with awarded contracts |  |[ ]  Post EIS award |
| Submit solicitation(s) to GSA for in-scope review | 1. GSA conducts review to ensure solicitation is within scope of the EIS contracts
 |[ ]  Post EIS award |
|  | 1. GSA may request requirement(s) to be redefined
 |  |  |
| Release FO solicitations to EIS contractors |  |[ ]  Mar 2019 |
| Update ATP and provide to GSA |  |[ ]  As appropriate |
| Conduct FO decision | 1. Evaluate offers from EIS contractors
 |[ ]  Oct 2017-Sept 2019; in parallel with BSS Testing |
|  | 1. Document findings
 |  |  |
|  | 1. Select contractor(s)
 |  |  |
|  | 1. Notify unsuccessful offerors
 |  |  |
|  | 1. Modify EIS contract, if required
 |  |  |
|  | 1. Debrief, as applicable
 |  |  |
| Business Support Systems (BSS) testing (EIS contractors) | 1. GSA tests each EIS contractor’s BSS in accordance with BSS functional requirements and security testing for GSA FISMA A&A
 |[ ]  Post EIS Award; in parallel with the FO process |
|  | 1. Optional: Agency conducts its own A&A
 |  |  |
| Receive notification of successful BSS testing and FISMA A&A (EIS contractors) | Issued by GSA CO |[ ]  Post EIS Award |
| Agency OCO awards EIS Task Order(s) |  |[ ]  Sep 2019 |
| Issue Service Orders (SOs) with EIS contractor | 1. Determine need for parallel operations of current service and replacement service
 |[ ]  ASAP after Task Order award |
|  | 1. Coordinate with Local Government Contacts for site preparation and access
 |  |  |
|  | 1. Identify service-order specific info such as Local Government Contacts, installation or activation dates, coordination with other vendors
 |  |  |
|  | 1. Identify all the CLINs
 |  |  |
|  | 1. Agency notifies the contractor the format (MS Word, Excel, etc.) in which it wants to receive order acknowledgments and notices
 |  |  |
|  | 1. Identify test and acceptance criteria for SOs
 |  |  |
| Establish accounts within the contractor's systems |  |[ ]  ASAP after Task Order award |
| Implement EIS service orders with EIS contractor | 1. Receive Service Order Acknowledgement (SOA) within one business day of SO receipt
 |[ ]  Within Provisioning SLAs |
|  | 1. Receive Service Order Rejection Notice (SORN) or Service Order Confirmation (SOC) within five business days of SO receipt
 |  |  |
|  | 1. Receive a Firm Order Commitment (FOC) date
 |  |  |
|  | 1. Receive Service Order Completion Notice (SOCN) upon successful completion of installation and testing
 |  |  |
|  | 1. Receive Other Notifications for administrative and service state changes as applicable
 |  |  |
|  | 1. Prepare for service cutovers (See Appendix G for more information)
 |  |  |
| Issue disconnects for current services on expiring contracts |  |[ ]  ASAP after replacement service is accepted |
| Agencies achieve 50% transition of services  |  |[ ]  Mar 2021 |
| Agencies achieve 90% transition of services |  | ☐ | Mar 2022 |
| Agencies achieve 100% transition of services (disconnected) | Agencies should plan to complete their transition by September 2022. Some agencies will have challenges completing by that timeframe and should work with GSA to mitigate the risks.  |[ ]  Sept 2022 |

Appendix F – Transition Order Sequencing

**F.1 Overview**

A collaboration team made up of representatives from Enterprise Infrastructure Solutions (EIS) contractors, GSA’s customer engagement organization, and GSA’s Transition Coordination Center was formed to collectively agree on guidance to share with agencies about sequencing EIS orders to efficiently accomplish the transition. The guidance provided by the collaboration team is intended to assist agencies with the implementation of their transition to EIS by providing an extensive listing of considerations.

**F.2 Factors for Order Sequencing Decisions**

Order sequencing is dependent on services contained in Task Order (TO) awards. Order sequencing should be determined by the agency following discussions with those EIS contractor(s) awarded the agency TOs; the approach must be customized to meet that agency’s needs.

Agencies are encouraged to start with the “big picture” before refining details to effectively sequence transition orders. Consider factors, such as:

* Attributes of Services to Transition (Section 2.1)
* Inventory (Section 2.2)
* Order Sequencing Considerations (Section 2.3).

***F.2.1 Attributes of Services to Transition***

As an initial step for order sequencing, it is recommended that agencies take the time to evaluate each category of service they use against three major attributes:

* 1. *Mission Criticality*
	2. *Technological and Implementation Complexity*
	3. *Volume of Individual Services*

By conducting this exercise, agencies will gain an understanding of the entirety of their transition challenge, thus aiding in making decisions on order sequencing.

One way to visualize and organize a portfolio of services based on the attributes is through use of a bubble chart. Figure 1 provides an example of how an agency’s services might be portrayed using this approach. To produce this chart will require a collaborative effort between subject matter experts from both the agency and the EIS contractor.



ILLUSTRATIVE EXAMPLE

Figure F-1. *Example Bubble Chart*

Agencies are encouraged to create such a portfolio management view for their own use. The value of this exercise is that it:

* Forces the agency and its contractor(s) to consider all the attributes; and
* Can serve as a means to communicate to senior agency officials the basis by which sequencing decisions have been made.

***F.2.2 Inventory***

Agencies must ensure that all services in their expiring contracts inventory are covered in transition project plans. Keep in mind, there is no set formula that applies to all agencies.

***F.2.3 Order Sequencing Considerations***

Table 1 provides a list of order sequencing considerations that should be reviewed and prioritized by the agencies and EIS contractors to drive final decisions on sequencing.

***Note:*** This list has been organized in alphabetical order.

Table F-1. *Order Sequencing Considerations*

| Considerations | Notes |
| --- | --- |
| Agency Priorities | Mission critical factors should receive the highest priority. Examples include locations immediately needing extra bandwidth, security issues awaiting action, implementation of new applications or services. |
| Buildings with No Current Services (no transition—new install) | Agencies with this situation will likely have to include these buildings/locations in their sequencing of orders based on occupancy target dates. |
| Complex Services  | While other services are transitioned more quickly, agencies should consider establishing parallel project teams to ensure complex services are addressed early in the transition. Examples include: Cybersecurity Team, Call Center Team, and Data Network Team. |
| Coordinated Site Visits | When sequencing orders, agencies should make every attempt to coordinate schedules for site visits to make efficient use of their site resources. |
| Cost Savings  | Agencies should factor in their ability to realize cost savings through lower monthly recurring charges, especially if non-recurring charges for these services have been waived.  |
| Diversity | Diversity is a factor that frequently takes additional time to address; therefore, agencies should identify locations requiring diversity, and begin activities as early in the transition as possible. |
| Implementations of Orders on Expiring Contracts  | Orders that are “in process” on expiring contracts should be completed before engaging those sites in transition. Agencies should be aware of pending implementations and schedule transition accordingly. |
| International Locations | Delivery intervals for international locations frequently exceed CONUS intervals. Locations in underdeveloped countries can have exceptionally long intervals, clearing personnel may require unspecified security procedures, and delivering equipment to many countries can have unique customs requirements that take time to resolve. Therefore, international orders should be placed early. |
| Learning Curve and Pilots | When implementing new technology, lessons learned recommend performing pilot implementations to prove not only the technology, but implementation processes before attempting to scale delivery. |
| Limit MACDs | As much as practical, agencies should strive to limit moves, adds, changes, and disconnects (MACDs) during transition, especially at sites that are actively engaged in new service implementation activities. A common mechanism employed is a “freeze period.” Agencies considering a freeze period should weigh the ability to enforce compliance. |
| Local Voice Service | The transition of local services can be challenging, as processes are not universal across all local providers. Challenges include local number portability (LNP), Primary Interexchange Carrier (PIC) change, generation of billing from a default long distance carrier (casual billing), Back Office Transition (BOT), and dependencies from different contract sub-organizations (unregulated and regulated entities). Given these complexities, this is an area where agencies should consider a dedicated transition team. |
| Multiple EIS Task Orders  | When determining the sequence of placing orders, agencies should consider how work related to multiple TOs (from a single EIS contractor or multiple EIS contractors) might adversely impact a site. |
| Network Topology | Agencies should ensure they align with their EIS contractor(s) on how the network topology may necessitate a specific sequencing of orders. A common example would be a hierarchical structure that incorporates hub and spoke locations, where hubs need to be installed before spokes. |
| Physical Buildout Support | Locations with known physical deficiencies (wiring, pathways, equipment, and special construction) should be addressed as early as possible in the transition, as these deficiencies have the potential to create significant delays. Often these requirements are not known until an order is placed, facility availability is assessed, and site surveys are conducted.  |
| Public Impacting  | Transition of services that are public impacting (access to web sites, toll free services, and contact centers), should receive extraordinary attention. In sequencing these orders, care should be given to include time for extensive testing and procedures for fallback, failover, or overflow to minimize service interruptions. |
| Quick Wins and High Visibility | Large, new task orders that are high-visibility often carry the political necessity of delivering quick wins. If this is the case with an agency, collaboration with the EIS contractor(s) can identify these for delivery early in the transition order sequencing. |
| Seasonal or Mission Critical Blackout Periods  | Agencies with planned blackout periods must factor these timeframes into order placement in order to avoid disruptions. |
| Simple Implementations | Given the guidance that complex implementations should be addressed early, agencies should identify simple implementations and consider executing these as projects in parallel with complex projects, or as “schedule fillers” to ensure continuous transition progress. |
| Timing of Budget Availability | Sequencing of orders may be impacted by non-recurring charges and the timing of budget availability to fund these costs. |
| Transition Approach | There are many different ways an agency can organize the transition: geography, technology, mission, organizational, or a combination of these. The approach should be carefully determined with the EIS contractor(s) to ensure a smooth transition. When applying order sequencing against an approach, the team should not overlook simple decisions. For example, with an organizational approach, who is ready to move first? |
| Using Third-Party Contracting Support | Any agency using third-party contracting support (such as the Bureau of Fiscal Services or Department of the Interior) should account for possible delays in ordering timeframes |

Appendix G – Cutover Guidance

**G.1 Overview**

GSA has prepared cutover guidance to assist agencies with planning the transition of services to EIS. This guidance covers cutover or “cut” types, planning considerations, limitations, and risks. Parallel cuts are recommended, when possible, in order to protect mission critical operations.

The descriptions below are general to most IT/telecom cutovers for services, circuits, and connections. Not all aspects presented apply to all situations. For example, data connection cutovers may require testing of all applications using a new transport service, while voice cutovers require a different set of testing considerations.

**G.2 Service Cutover Definitions**

***G.2.1 Hot Cut***

A hot cut is a virtually instantaneous replacement of one service with another. For the purposes of EIS, hot cuts can relate to almost any service, including: voice, data, toll-free numbers, local exchange lines, Ethernet and private branch exchange stations. Hot cuts may cause site outages averaging 15 to 30 minutes (and possibly one hour or more), depending on the challenges associated with the order.

Examples of situations where agencies consider hot cuts include:

* Swapping dedicated access circuits for wide area networks
* Transferring a customer's telephone number and dial tone from the Incumbent Local Exchange Carrier (ILEC) switch to a Competitive Local Exchange Carrier (CLEC) switch
* Ethernet upgrades requiring a rehome
* Copper to fiber conversions
* Virtual Local Area Network (VLAN) changes
* New extensions and inside wiring from the demarcation point.

***G.2.2 Parallel Cut***

A parallel cut leaves the legacy system functional until the new system is installed and determined to be acceptable. This type of circuit activation can occur during regular business hours since there is no disruption to the existing service. Once the agency or contractor confirms the new circuit is functioning properly, traffic can be cutover to a new circuit through routing changes, either all at once or in segments. The current service then remains connected in a standby mode for some period of time (24-96 hours) in case of failure of the new service.

Parallel cuts require equipment space for the new service, or additional equipment to be installed before scheduled test events. Disconnect of the old service is typically scheduled days or weeks ahead and will often be performed automatically at the scheduled time, unless cancelled. Agencies should separate activation and disconnect by at least 24-48 hours to avoid loss of service.

**G.3 Considerations**

Cutovers demand early attention from agency telecommunications managers, as telecommunications contractors offer a wide range of approaches. Agencies should balance their mission requirements and budget with physical limitations, cost, and desired user experience. Cutovers should be properly planned and executed using the cutover phases outlined below to minimize transition delays and improve the likelihood of cutover success.

***G.3.1 Physical Limitations***

In situations where physical capacity will not allow for parallel services or equipment to be installed, a hot cut may be the only alternative. An example would be the reuse of local access in locations where new access cannot be physically provided.

In some cases, the contractor may be able to provide a temporary or backup wireless connection for the cutover period to allow parallel operations.

***G.3.2 Cost***

Agencies should include the costs associated with the risk of service loss in their cost evaluation. While a parallel cut can be more expensive up-front, the difference may be insignificant when considering the cost impact of a disruption of services to mission critical operations.

***G.3.3 User Experience***

When upgrading from an old or expiring technology, sometimes it is advisable not to permit parallel operations, as users tend to remain on the old service simply because they are comfortable. In a hot cut to new technology, special care must be taken to provide a fallback plan should the new technology fail to meet requirements or otherwise disrupt operations.

***G.3.4 Coordination of Multiple Providers***

EIS contractors may outsource work to other providers, thereby increasing the need for coordination across multiple parties at multiple levels. Agencies should define cutover requirements in the FO solicitation and include language that requires communication of requirements to all providers.

* Depending on the contractor, a cutover may require multiple service orders, which must be correlated within the contractor’s system and coordinated between providers.
* Processes by contractor may vary based on volume of work. For example, many contractors will require project treatment for a group of orders; others will classify orders as “batch cuts,” meaning orders submitted as part of the batch are held until a critical mass of orders is reached.

***G.3.5 Site Location***

Site location may also impact the complexity of the transition and present a risk to service transition.

* Cutover processes often vary depending on the geographic area. Agencies cannot assume that a process used by a contractor in one geographic area will apply to that same contractor in another geographic area.
* Unmanned sites may require agency escort or other means of providing site access to contractor personnel. Lack of contractor access may result in cutover delays, cancellations, and contractor charges.
* A best practice is to have agency personnel available on-site to reboot and/or reconfigure equipment.

**G.4 Risks and Mitigation Strategies**

Since the most critical risk to an agency is loss of service, a parallel cut should be used whenever possible. Coordination among multiple contractors, locations, and involved processes may also contribute to the complexity of a service transition and present a risk to agencies. Table 2 identifies potential risks and mitigation strategies.

Table G-1. *Risks and Mitigation Strategies*

| **Description of Risk** | **Mitigation Strategy** |
| --- | --- |
| Loss in service impacts mission critical operations.  | Transition services using a parallel cut. |
| Coordination among multiple providers increases transition complexity. | When establishing the cutover team, ensure all providers (existing and new) are represented. |
| Cutover process differs by geographic area, increasing transition complexity.Agencies cannot assume that a process used by a contractor in one geographic area applies to another geographic area for the same contractor. | Work with the contractor to obtain a complete understanding of cutover practices by geographic area. |
| Batch cutovers delay service transition progress if the defined minimum for batch size is not reached. | Agencies should provide the scope of their cutover requests to all contractors with mandatory flow-down to other providers, such as the LEC. |
| Access unavailability results in cutover delays, cancellations, or contractor charges. | Determine and coordinate site access requirements ahead of time. |
| Unsuccessful cutover. | Ensure a fallback process is planned and available before beginning. |
| Replacement service requires new operating procedures within agency. | Review service characteristics with contractor and agency personnel and revise operating procedures as needed. |

**G.5 Cutover Task Checklist**

Items listed in Table 2 cover elements pertaining to all types of telecommunications cutovers. Agencies should adapt the list to their unique situation.

Table G-2. *Cutover Task Checklist*

| Cutover Phase |  Tasks |
| --- | --- |
| Organize the Project | * Set project objectives
* Establish cutover team
	+ Consider if GSA is a stakeholder
	+ Ensure all providers (both existing and new) are represented
* Establish key cutover dates and milestones
* Hold a kick-off meeting
* Develop task lists
* Determine constraints (military bases, airports, campus environments, new construction, standard maintenance windows, critical operating timeframes)
* Perform a cost/benefit analysis supporting the cutover
* Determine measures of success
 |
| Develop Requirements | * Determine system requirements
* Determine feature requirements
* Conduct analysis of new services vs. a hybrid system that reuses part of the legacy network
* If a parallel cutover: determine the length of time parallel service is needed; Factor in pre-cutover testing (24-96 hours) and post-cutover coverage for continued testing and user support (24-96 hours)
* Determine if diversity/redundancy is required
* Determine the adequacy of inside wiring
* Determine landlord and building management’s approval requirements
* Determine access type and entrance facilities, especially when converting to Ethernet, specify whether electrical or optical
* Determine site requirement – space, rack, power, Heating, Ventilating, and Air-Conditioning (HVAC)
* Determine equipment requirements
	+ If parallel cutover, determine if existing equipment will support parallel operations
* Identify equipment locations
	+ Floor Plans: Identify equipment and cubicle numbers, outlets and room locations
* Determine station requirements
* Determine trunk and bandwidth requirements
* Determine attendant console requirements
* Determine call accounting requirements
 |
| Plan the Cutover | * Coordinate building/room access
* Confirm availability of critical personnel
* Determine facility transition methods
* Develop training plan and new operating procedures
* Develop station numbering plan
* Determine protection requirements
* Develop cutover methods
* Develop cutover schedule
	+ Cutover Timing: Hot cuts should always be conducted after the close of business or during off-peak usage times (access may be required, and additional charges may apply for after-hours support by providers)
	+ Depending on the agency’s level of risk tolerance, parallel cutovers can be conducted during the business day
	+ Consider impacts from agency mission blackout dates and weather conditions
* Develop pre-cutover and post-cutover testing methods and checklists
* Develop security and anti-toll fraud measures
* Develop change control procedures
* Identify critical facilities (users, stations, applications)
* Identify power-fail procedures
* Determine station terminating arrangements
* Develop class-of-service and restriction plans
* Develop voicemail plans
* Compile station records
* Assign station numbers
* Develop intercept plans
* Reprint directories
* Reprint stationery
* Develop wiring plans
* Determine and publicize “freeze” dates
* Develop contingency fallback or failover plan: This plan allows for an alternative procedure in case the cutover schedule is delayed or unsuccessful. Points to be considered in a contingency plan include:
	+ What other projects depend on the completion of this plan?
	+ What penalty will be paid if this plan is delayed?
	+ What is the probability of delay?
	+ What factors could cause the cutover to be delayed?
	+ What alternatives are available to hold the schedule despite delays?
	+ What conditions demand a fallback or failover decision?
	+ Who makes the fallback or failover decision?
 |
| Prepare the Equipment Facilities | * Select location
* Assure the building possesses all the necessary facilities for a successful cutover
* Develop equipment room drawings
* Prepare equipment room
* Prepare electrical wiring
* Prepare HVAC
 |
| Select and Order Network Facilities | * Determine network facility requirements
* Place orders for services
 |
| Order Equipment | * Place orders for telecommunications equipment
* Ensure POC is available to accept and store equipment securely
* Receive equipment
 |
| Install Cabling | * Design distribution system
* Place and test station wiring
* Place and test extended demarcation wiring
 |
| Install Equipment | * Ensure required inside wiring has been installed and tested
* Conduct station reviews
* Assign station connections
* Place station equipment
* Install start-up software
* Install equipment
* Test equipment
* Conduct initial circuit testing
* Prepare station translations
* Prepare trunk translations
* Program Automatic Route Selection (ARS)
* Prepare toll-fraud barriers
* Set up voice mail boxes
* Initialize call accounting software
* Assure security controls are in place
* Assure help desk readiness
* Document trouble-reporting procedures
 |
| Train Users | * Develop user training plans
* Develop attendant training plans
* Prepare training room
* Prepare training schedule
* Train users
* Provide all new circuit and equipment information to the affected Network Management Organization
 |
| Cutover System | * Perform pre-cutover tests
* Perform pre-cutover network facility tests
* Advise agency/customers of time/date and set expectations
* Cutover system
* Test critical facilities/stations
 |
| Accept System | * Perform post-cutover/acceptance tests
	+ Testing should be based on a manual of performance tests that the system must meet before it is turned up for service
* Prepare records; the telecom manager must compile, review and file all documentation. The documentation should include the following:
	+ System operation and maintenance manuals
	+ Station wiring diagrams
	+ Trunk and station cross-connect lists, including cable and pair assignments
	+ Class-of-restriction and class-of-service assignments
	+ Feature assignment lists
	+ Port assignment lists
	+ Hunt and pickup group assignments
	+ User assignment information
	+ Extension number
	+ Room number
	+ Answering location
	+ Features
	+ Restrictions
* Provide appropriate “as-built” documentation to the affected Network Management Organization
* Conduct follow-up training
* Review trunk and circuit usage data
* Verify billing from all contractors
	+ All components of disconnected service are no longer billing (features, equipment)
	+ Service billing aligns with task order pricing and is correct for the service location
* Inventory equipment
* Remove old equipment and wiring
* Clean up work areas
* Accept the system
 |
| Measure Results | * Record and assess results against measures of success
	+ It is important to remember that the success or failure of the cutover will be measured by the amount of disruption experienced during the first few days after the cutover
 |